## Sheet1
MC | A project has expenditure of 180 lacs and the revenues at the end of each year are 64, 80, 100, 125 and 105 lacs. The Payback period is estimated as ____ years | 2.45 | Incorrect | 2.54 | Incorrect | 2.28 | Incorrect | 2.36 | Correct
MC | A project has expenditure of 180 lacs and the revenues at the end of each year are 64, 80, 100, 125 and 105 lacs. The ROI for the project is _____ percent | 32.67 | Correct | 35.67 | Incorrect | 25.67 | Incorrect | 33.33 | Incorrect
MC | A project has expenditure of 180 lacs and the revenues at the end of each year are 64, 80, 100, 125 and 105 lacs. The NPV assuming 12.5 percent discount rate is _____ lacs | 141.89 | Incorrect | 143.37 | Incorrect | 146.63 | Correct | 151.89 | Incorrect
MC | A project has expenditure of 180 lacs and the revenues at the end of each year are 64, 80, 100, 125 and 105 lacs. The discount rate for which NPV is nearly zero is ____ | 41.5 | Incorrect | 44.4 | Incorrect | 38.5 |  | 35.5 | Incorrect
MC | A project has cashflows of -100000, 10000, 10000, 10000, 20000, 100000 (all in dollars) for year 0, 1, 2, 3, 4 and 5 respectively. The Payback period is estimated as ____ years | 3.5 | Incorrect | 4.25 | Incorrect | 4.8 | Incorrect | 4.5 | Correct
MC | A project has cashflows of -100000, 10000, 10000, 10000, 20000, 100000 (all in dollars) for year 0, 1, 2, 3, 4 and 5 respectively. The ROI for the project is _____ percent | 9.5 | Incorrect | 10 | Correct | 10.5 | Incorrect | 11.5 | Incorrect
MC | A project has cashflows of -100000, 10000, 10000, 10000, 20000, 100000 (all in dollars) for year 0, 1, 2, 3, 4 and 5 respectively.NPV assuming 10 percent discount rate is ____ | 575 | Incorrect | 588 | Incorrect | 618 | Correct | 648 | Incorrect
MC | The average staffing size for a 200 KLOC project using COCOMO Model is ___ persons | 38.67 | Correct | 36.63 | Incorrect | 35.33 | Incorrect | 30.88 | Incorrect
MC | The effort for a project of size 500 KLOC using COCOMO Model is ________ PM | 6328 | Incorrect | 6350 | Incorrect | 6268 | Incorrect | 6238 | Correct
MC | The development time for a project of size 500 KLOC using COCOMO Model is ______ | 41 | Correct | 45 | Incorrect | 38 | Incorrect | 46 | Incorrect
MC | Productivity for a project of 400 KLOC using COCOMO Model is _______ LOC/PM | 75.3 | Incorrect | 74.9 | Incorrect | 83.8 | Correct | 76.6 | Incorrect
MC | The average staffing size for a 400 KLOC project using basic COCOMO Model is ___ persons | 131.8 | Incorrect | 125.6 | Correct | 135.4 | Incorrect | 130.9 | Incorrect
MC | A program has 5 EIs of simple type, 4 EOs of average type, 4 EQs of complex type, 3 ILFs of average type and 4 EIFs of complex type. The complexity adjustment factors are to be taken as average. The FP for this program is ____ | 128 | Incorrect | 131 | Incorrect | 138 | Correct | 145 | Incorrect
MC | A program has 5 EIs of simple type, 4 EOs of average type, 4 EQs of complex type, 3 ILFs of average type and 4 EIFs of complex type. The complexity adjustment factors are to be taken as average. The UFP for this program is ____ | 125 | Incorrect | 129 | Correct | 121 | Incorrect | 119 | Incorrect
MC | A system has 15 user inputs (Average), 10 user outputs (High), 5 user inquiries (High), 8 internal logical files (Low) and 4 external interface (High). The UFP Count is ____ | 236 | Incorrect | 248 | Incorrect | 244 | Incorrect | 256 | Correct
MC | Assume that the size of an organic type software product has been estimated to be 32,000 lines of source code. Assume that the average salary of software engineers be Rs. 15,000/- per month. Determine the effort required to develop the software product and the nominal development time.From the basic COCOMO estimation formula for organic software:From the basic COCOMO estimation formula for organic software: EFFORT is | 96 | Incorrect | 91 | Correct | 196 | Incorrect | 191 | Correct
MC | Assume that the size of an organic type software product has been estimated to be 32,000 lines of source code. Assume that the average salary of software engineers be Rs. 15,000/- per month. Determine the effort required to develop the software product and the nominal development time.From the basic COCOMO estimation formula for organic software:From the basic COCOMO estimation formula for organic software: Nominal Development Time is | 14 months | Correct | 12 months | Incorrect | 15 months | Incorrect | 19 months | Incorrect
MC | Project A is to be a 32,000 DSI semi-detached software. It is in a mission critical area, so the reliability is high (RELY=high=1.15). Then calculate:EFFORT | 268 | Incorrect | 168 | Incorrect | 167 | Correct | 267 | Incorrect
MC | Project A is to be a 32,000 DSI semi-detached software. It is in a mission critical area, so the reliability is high (RELY=high=1.15). Then calculate:SCHEDULE | 14 months | Incorrect | 12 months | Incorrect | 15 months | Correct | 19 months | Incorrect
MC | Project A is to be a 32,000 DSI semi-detached software. It is in a mission critical area, so the reliability is high (RELY=high=1.15). Then calculate:Productivity | 192 | Correct | 178 | Incorrect | 191 | Incorrect | 198 | Incorrect
MC | A company wants to start a Project and to calculate its feasibility,The Projects uses the model as an equation to estimate the desired values such as cost, time, effort, etc. They all depend on the same variable used as predictor (say, size). mind Company deduced that the project they are using is of size 500 KLOC, Based on the data given calculate EFFORT | 453.0751 | Correct | 553.0751 | Incorrect | 653.0751 | Incorrect | 463.0751 | Incorrect
MC | A company wants to start a Project and to calculate its feasibility,The Projects uses the model as an equation to estimate the desired values such as cost, time, effort, etc. They all depend on the same variable used as predictor (say, size). mind Company deduced that the project they are using is of size 500 KLOC, Based on the data given if Company need to calculate what will be the documentation size | 3812.4073 | Incorrect | 6757.1276 | Incorrect | 8164.8195 | Correct | 9012.7653 | Incorrect
MC | A company wants to start a Project and to calculate its feasibility,The Projects uses the model as an equation to estimate the desired values such as cost, time, effort, etc. They all depend on the same variable used as predictor (say, size). mind Company deduced that the project they are using is of size 500 KLOC, Based on the data given what will be the duration of the project | 565.12 | Incorrect | 45.890 | Incorrect | 23.1468 | Correct | 314.765 | Incorrect
MC | A company wants to start a Project and to calculate its feasibility,There is another method which states that there is some models which are often based on equation (i), they actually depend on several variables representing various aspects of the software development environment, for example method used, user participation, customer oriented changes, memory constraints, etc.Company deduced that the project they are using is of size 500 KLOC, Based on the data given Effort required is | 3321.8752 | Incorrect | 1486.1617 | Correct | 1678.3452 | Incorrect | 2345.1234 | Incorrect
MC | A company wants to start a Project and to calculate its feasibility,There is another method which states that there is some models which are often based on equation (i), they actually depend on several variables representing various aspects of the software development environment, for example method used, user participation, customer oriented changes, memory constraints, etc.Company deduced that the project they are using is of size 500 KLOC, Based on the data given what will be the duration of the project | 67.1234 | Incorrect | 89.5678 | Incorrect | 651.8901 | Incorrect | 38.4072 | Correct
MC
MC